## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a founder, I want to enter my idea, target customer, and problem so the system can validate it | MUST HAVE |  | Yasaswini | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a team, we want a documented system architecture so everyone builds against a shared contract | MUST HAVE |  | Yasaswini | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a founder, I want a Web Search Agent that searches live across 5 research angles for grounded market data | MUST HAVE | US-02 | Yasaswini | 3- Completed
Sprint 1 | Sprint 1 | US-03b | As a founder, I want Tavily used as the primary search provider for high-quality relevance scoring | MUST HAVE | US-03 | Varshini | 3- Completed
Sprint 1 | Sprint 1 | US-04 | As a founder, I want a free fallback search chain so the tool works without a paid API key | SHOULD HAVE | US-03 | Yasaswini | 3- Completed
Sprint 1 | Sprint 1 | US-05 | As a founder, I want academic/research-paper sources filtered out for useful market signal | COULD HAVE | US-03 | Yasaswini | 3- Completed
Sprint 1 | Sprint 1 | US-06 | As a founder, I want a backend API (POST /validate) that runs my submission and returns results | MUST HAVE | US-02, US-03 | Yasaswini | 3- Completed
Sprint 1 | Sprint 1 | US-07 | As a founder, I want results grouped by research angle with source links I can verify | MUST HAVE | US-01, US-06 | Anu Kumari | 3- Completed
Sprint 1 | Sprint 1 | US-08 | As a founder, I want clear error/empty states so the app never looks broken | MUST HAVE | US-06, US-07 | Yasaswini | 3- Completed
Sprint 1 | Sprint 1 | US-09 | As a team, we want both services deployed live on Render so the app is demoable | MUST HAVE | US-06, US-07 | Yasaswini | 3- Completed
Sprint 2 | Sprint 2 | US-10 | As a founder, I want the Market Opportunity Agent to include pain points, motivations, and buying behavior per segment | MUST HAVE | US-03 | Yasaswini | 3- Completed
Sprint 2 | Sprint 2 | US-11 | As a founder, I want a Competitor Discovery & Comparison Agent so I can see existing players and gaps | MUST HAVE | US-03 | Yasaswini | 3- Completed
Sprint 2 | Sprint 2 | US-12 | As a team, we want a 3-node pipeline with graceful partial-failure handling so one agent failing doesn't break the request | MUST HAVE | US-10, US-11 | Yalene | 3- Completed
Sprint 2 | Sprint 2 | US-13 | As a founder, I want to see market opportunity and competitor data clearly displayed, with a fallback if a section fails | MUST HAVE | US-10, US-11 | Yasaswini | 3- Completed
Sprint 2 | Sprint 2 | US-14 | As a team, we want the pipeline validated on 3 different-industry ideas and failure paths tested, and documented | MUST HAVE | US-12, US-13 | Yasaswini,Varshini,Yalene | 2- In Progress
Sprint 2 | Sprint 2 | US-15 | As a founder, I want a single 0-100 Market Opportunity Score so I don't have to synthesize raw numbers myself | SHOULD HAVE | US-10 | Sashi | 3- Completed
Sprint 2 | Sprint 2 | US-16 | As a founder, I want a 3x3 competitor positioning snapshot (price vs. features) so I can compare at a glance | COULD HAVE | US-11 | Yasaswini | 3- Completed
Sprint 2 | Sprint 2 | US-17 | As a founder, I want a cross-source confidence indicator so I know how much the sources agree | COULD HAVE |  | Yasaswini | 3- Completed
Sprint 3 | Sprint 3 | US-18 | As a founder, I want a SWOT and risk analysis grounded in market/competitor evidence so I understand strategic risk | MUST HAVE | US-10, US-11 | Yasaswini | 3- Completed
Sprint 3 | Sprint 3 | US-19 | As a founder, I want MVP feature recommendations prioritized from SWOT and market evidence so I know what to build first | MUST HAVE | US-18 | Yasaswini | 3- Completed
Sprint 3 | Sprint 3 | US-20 | As a founder, I want a Go-To-Market strategy (positioning, channels, early customer approach) grounded in my own market data | MUST HAVE | US-10, US-11, US-18 | Yasaswini | 3- Completed
Sprint 3 | Sprint 3 | US-21 | As a founder, I want a conversational advisor so I can ask follow-up questions about my validation results | MUST HAVE | US-06 | Yasaswini | 3- Completed
Sprint 3 | Sprint 3 | US-22 | As a founder, I want evidence-backed white-space/opportunity-gap analysis without an extra LLM call | SHOULD HAVE | US-10, US-11 | Yasaswini | 3- Completed
Sprint 3 | Sprint 3 | US-23 | As a founder, I want to download a polished PDF dossier of my full validation report | SHOULD HAVE | US-18, US-19, US-20 | Yasaswini | 3- Completed
Sprint 3 | Sprint 3 | US-24 | As a founder, I want a long-running validation emailed to me instead of waiting on a blocked page | COULD HAVE | US-06 | Yasaswini | 3- Completed
Sprint 3 | Sprint 3 | US-25 | As a founder, I want a bare 'AI X' idea phrasing to still return relevant results instead of generic AI-company noise | SHOULD HAVE | US-03 | Yasaswini | 3- Completed
Sprint 4 | Sprint 4 | US-26 | As a founder, I want every SWOT claim to cite the source(s) it's grounded in so I can verify it myself | MUST HAVE | US-18 | Yasaswini | 3- Completed
Sprint 4 | Sprint 4 | US-26b | As a founder, I want every GTM and MVP claim to cite its source(s) too, matching the SWOT pattern | MUST HAVE | US-26 | Yasaswini | 3- Completed
Sprint 4 | Sprint 4 | US-26c | As a founder, I want Market Opportunity claims to cite sources, and the shared schema validator to enforce it everywhere | MUST HAVE | US-26 | Yalene,Yasaswini | 3- Completed
Sprint 4 | Sprint 4 | US-26d | As a founder, I want a confidence dashboard (source coverage, agreement, recency) instead of a single confidence badge | MUST HAVE | US-26 | Yasaswini | 3- Completed
Sprint 4 | Sprint 4 | US-27 | As a founder, I want contradictory signals (e.g. high score with high-severity risks) surfaced, not hidden | SHOULD HAVE | US-26, US-26b, US-26c | Yalene | 3- Completed
Sprint 4 | Sprint 4 | US-28 | As a founder, I want my top risks turned into concrete validation experiments and a 7/30/90-day action plan | SHOULD HAVE | US-18, US-19, US-20 | Yasaswini | 3- Completed
Sprint 4 | Sprint 4 | US-29 | As a founder, I want one canonical report object assembled from every agent's output, ready for export and email | MUST HAVE | US-26, US-27, US-28 | Yasaswini | 3- Completed
Sprint 4 | Sprint 4 | US-30 | As a founder, I want to click a claim and see its citation, confidence, contradictions, and action plan in the UI | MUST HAVE | US-26, US-29 | Anu Kumari | 3- Completed
Sprint 4 | Sprint 4 | US-31 | As a team, we want the full pipeline tested end-to-end (incl. every failure path), tuned, and deployed before the deadline | MUST HAVE | US-26, US-27, US-28, US-29, US-30 | Yalene, Yasaswini | 3- Completed
Sprint 4 | Sprint 4 | US-32 | As a founder, I want the advisor to remember key pivots in our chat without resending the whole transcript each turn | COULD HAVE | US-21 | Yasaswini | 3- Completed
Sprint 4 | Sprint 4 | US-33 | As a founder, I want a quick-validation mode for a fast first read, and a deep mode for the full strategic report | COULD HAVE | US-26 | Yasaswini,Yalene | 3- Completed
Sprint 5 | Sprint 5 | US-34 | As a founder, I want Wikidata/iTunes enrichment to actually work so competitor cards show real company data | MUST HAVE | US-11 | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-35 | As a founder, I want CEO-bio, review-byline, and scraped-byline-merge text filtered out of competitor names so the list stays trustworthy | MUST HAVE | US-11 | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-36 | As a founder, I want competitors classified as direct/indirect so I can gauge real rivalry, not just a name list | SHOULD HAVE | US-11 | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-37 | As a team, we want search results blended across providers so one dominant low-quality page can't flood a query's results | SHOULD HAVE | US-03 | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-38 | As a team, we want the Groq/Gemini fallback chain to actually work (dead model reference, over-budget token request) instead of silently degrading | MUST HAVE | US-03 | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-39 | As a team, we want a node's error message preserved even if a later node also fails, so partial failures stay debuggable | SHOULD HAVE | US-12 | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-40 | As a team, we want our local branch reconciled against teammates' parallel fixes before merging, so we don't regress or duplicate already-shipped work | MUST HAVE |  | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-41 | As a team, we want CI to run the full automated test suite (backend + frontend) on every push/PR so regressions are caught before merge | MUST HAVE |  | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-42 | As a team, we want comprehensive automated test coverage across the pipeline (auth, scoring, competitors, PDF, LLM fallback) so every major code path is regression-tested | MUST HAVE | US-41 | Yasaswini,Team | 3- Completed
Sprint 6 | Sprint 5 | US-43 | As a founder, I want more competitors surfaced per report so I see the full competitive landscape, not just a handful | SHOULD HAVE | US-11 | Yasaswini | 3- Completed
Sprint 6 | Sprint 5 | US-44 | As a founder, I want the Opportunity/Viability scoring reviewed and refined per mentor feedback so the score better reflects real risk | SHOULD HAVE |  | Yasaswini | 3- Completed
Sprint 6 | Sprint 5 | US-45 | As a founder, I want real visual charts (not just tables) in the exported PDF so the report is easier to scan | SHOULD HAVE | US-23 | Yasaswini | 3- Completed
Sprint 6 | Sprint 5 | US-46 | As a team, we want a documented cloud-scaling plan and known-limitations writeup so we can discuss tradeoffs with stakeholders | COULD HAVE |  | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-47 | As a team, we want the database moved to Neon free Postgres with a verified data copy (no expiry, faster reads) | MUST HAVE | US-09 | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-48 | As a user, I want sign-in to be fast on the free instance (bcrypt cost 10, rehash on login) | SHOULD HAVE |  | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-49 | As a founder, I want overall confidence to reflect all cited sources and never show 0% when sources exist (blended headline) | MUST HAVE | US-26d | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-50 | As a founder, I want competitor searches built from the idea's domain terms, and non-repeating fallback threats | MUST HAVE | US-11 | Yasaswini | 3- Completed
Sprint 5 | Sprint 5 | US-51 | As a team, we want degraded (AI-unavailable) reports not cached, so re-running an idea gets a fresh result | SHOULD HAVE | US-33 | Yasaswini | 3- Completed
Sprint 6 | Sprint 6 | US-52 | As a team, we want a load test with 5-6 concurrent users run and documented (plan in docs/load-testing-plan.md) | SHOULD HAVE | US-46 | Yasaswini | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 216 | 83 | 32 | 24 | 23 | 23 | 8 | 6 | 3 | 8 | 8 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-02 | T-01 | Write docs/architecture.md (system overview, data flow) | 2026-08-25 | 2026-08-25 | Yasaswini | Design | 3- Completed | 4 | Day 1: 4
US-02 | T-02 | Lock POST /validate API contract | 2026-08-25 | 2026-08-25 | Yasaswini | Design | 3- Completed | 1 | bar: Day 1
US-01 | T-03 | Scaffold React + Tailwind app, build IdeaForm | 2026-08-25 | 2026-08-26 | Yasaswini | Coding | 3- Completed | 4 | Day 1: 4
US-03 | T-04 | Build 5-angle query expansion in retrieval.py | 2026-08-26 | 2026-08-26 | Yasaswini | Coding | 3- Completed | 3 | Day 2: 3
US-03b | T-05 | Integrate Tavily API in tools.py | 2026-08-26 | 2026-08-26 | Varshini | Coding | 3- Completed | 2 | Day 2: 2
US-04 | T-06 | Implement DuckDuckGo/Wikipedia/HN fallback chain | 2026-08-26 | 2026-08-26 | Yasaswini | Coding | 3- Completed | 3 | Day 2: 3
US-05 | T-07 | Filter academic/research-paper domains from results | 2026-08-27 | 2026-08-27 | Yasaswini | Coding | 3- Completed | 1 | bar: Day 3
US-06 | T-08 | Build FastAPI POST /validate endpoint | 2026-08-27 | 2026-08-27 | Yasaswini | Coding | 3- Completed | 3 | Day 3: 3
US-06 | T-09 | Add error handling (400 empty idea, 502 all sources fail) | 2026-08-27 | 2026-08-27 | Yasaswini | Coding | 3- Completed | 2 | Day 3: 2
US-07 | T-10 | Build ValidationResults component (grouped by angle) | 2026-08-26 | 2026-08-26 | Anu Kumari | Coding | 3- Completed | 2 | Day 2: 2
US-07 | T-11 | Wire results display to backend response shape | 2026-08-27 | 2026-08-27 | Yasaswini | Coding | 3- Completed | 2 | Day 3: 2
US-08 | T-12 | Build EmptyState + ErrorState components | 2026-08-27 | 2026-08-27 | Yasaswini | Coding | 3- Completed | 2 | Day 3: 2
US-06 | T-13 | End-to-end local integration test | 2026-08-27 | 2026-08-27 | Yasaswini | Integration Test | 3- Completed | 2 | Day 3: 2
US-09 | T-14 | Configure render.yaml, deploy both services | 2026-08-27 | 2026-08-28 | Yasaswini | Build | 3- Completed | 3 | Day 4: 3
US-09 | T-15 | Manual test pass: empty idea, API failure, mobile viewport | 2026-08-28 | 2026-08-28 | Yasaswini | System Test | 3- Completed | 2 | Day 4: 2
US-02 | T-16 | Update README with final architecture | 2026-08-28 | 2026-08-28 | Yasaswini | Others | 3- Completed | 1 | bar: Day 4
SPRINT 2 BACKLOG
US-10 | T-17 | Fix Market Opportunity Agent segment fields (painPoints/motivations/buyingBehavior) | 2026-09-01 | 2026-09-01 | Yasaswini | Coding | 3- Completed | 4 | Day 1: 4
US-11 | T-18 | Build Competitor Discovery Agent (competitor_agent.py), same pattern as market_agent.py | 2026-09-01 | 2026-09-01 | Yasaswini | Coding | 3- Completed | 4 | Day 1: 4
US-12 | T-19 | Wire 3rd LangGraph node (competitor_discovery) + partial-failure handling + logging | 2026-09-02 | 2026-09-03 | Yalene | Coding | 2- In Progress | 5 | Day 2: 5
US-13 | T-20 | Build frontend for market opportunity + competitor data, with null/error section states | 2026-09-02 | 2026-09-04 | Anu Kumari | Coding | 2- In Progress | 5 | Day 2: 5
US-17 | T-21 | Build cross-source confidence indicator (backend aggregation + frontend badge) | 2026-09-02 | 2026-09-02 | Sashi | Coding | 1- Not Started | 3 | Day 2: 3
US-15 | T-22 | Add Market Opportunity Score (0-100) to market_agent.py output | 2026-09-03 | 2026-09-03 | Sashi | Coding | 3- Completed | 2 | Day 3: 2
US-16 | T-23 | Populate estimatedPrice/featureBreadth fields in competitor_agent.py | 2026-09-04 | 2026-09-04 | Sashi | Coding | 3- Completed | 2 | Day 4: 2
US-16 | T-24 | Build competitor positioning 3x3 grid UI | 2026-09-04 | 2026-09-04 | Yasaswini | Coding | 3- Completed | 3 | Day 4: 3
US-14 | T-25 | Failure-injection testing on all 3 pipeline nodes + error-state UI verification | 2026-09-05 | 2026-09-05 | Yasaswini,Varshini | System Test | 2- In Progress | 4 | Day 5: 4
US-14 | T-26 | Run pipeline on 3 startup ideas across different industries, document findings | 2026-09-05 | 2026-09-06 | Varshini | System Test | 1- Not Started | 6 | Day 5: 6
US-12 | T-27 | Add try/except in market_opportunity_node and competitor_discovery_node + populate an errors field in the /validate response (required partial-failure handling, currently missing) | 2026-09-03 | 2026-09-03 | Yalene | Coding | 3- Completed | 2 | Day 3: 2
US-12 | T-28 | Add intermediate-result logging at each pipeline node boundary (currently only web_search logs) | 2026-09-06 | 2026-09-03 | Yasaswini | Coding | 3- Completed | 1 | bar: Day 3
SPRINT 3 BACKLOG
US-22 | T-29 | Build white_space.py (deterministic opportunity-gap analysis, no extra LLM call) | 2026-09-15 | 2026-09-15 | Yasaswini | Coding | 3- Completed | 3 | Day 1: 3
US-18 | T-30 | Build swot_agent.py (LLM crew + JSON validation) and deterministic_swot fallback | 2026-09-16 | 2026-09-16 | Yasaswini | Coding | 3- Completed | 4 | Day 2: 3
US-19 | T-31 | Build mvp_agent.py and deterministic_mvp fallback | 2026-09-16 | 2026-09-16 | Yasaswini | Coding | 3- Completed | 3 | Day 2: 3; Day 3: 1
US-20 | T-32 | Build gtm_agent.py and deterministic_gtm fallback | 2026-09-16 | 2026-09-16 | Yasaswini | Coding | 3- Completed | 3 | Day 3: 2; Day 4: 1
US-21 | T-33 | Build chat_graph.py + session_store.py, wire POST /chat | 2026-09-16 | 2026-09-16 | Yasaswini | Coding | 3- Completed | 4 | Day 3: 2; Day 4: 2
US-23 | T-34 | Build pdf_exporter.py (ReportLab) + /export-pdf and /validate/{id}/pdf endpoints | 2026-09-16 | 2026-09-16 | Yasaswini | Build | 3- Completed | 3 | Day 4: 3
US-24 | T-35 | Build email_delivery.py + job_store.py, async /validate path, UI email checkbox | 2026-09-16 | 2026-09-16 | Yasaswini | Coding | 3- Completed | 4 | Day 4: 3; Day 5: 1
US-25 | T-36 | Fix retrieval.py: bare 'AI X' phrasing was swamping queries with generic AI-company results | 2026-09-16 | 2026-09-16 | Yasaswini | Coding | 3- Completed | 1 | bar: Day 5
US-18 | T-37 | Reconcile two independent Milestone 3 branches, merge into staging (kept staging's PDF export) | 2026-09-16 | 2026-09-16 | Yasaswini | Others | 3- Completed | 2 | Day 5: 2
SPRINT 4 BACKLOG
US-26 | T-38 | Add sourceIds to swot_agent.py's LLM prompt, JSON schema, and deterministic fallback | 2026-09-18 | 2026-09-18 | Yasaswini | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US-26 | T-39 | Fix downstream sourceIds-shape breakage (deterministic_mvp, email_delivery, pdf_exporter) + tests | 2026-09-18 | 2026-09-18 | Yasaswini | Coding | 3- Completed | 2 | Day 2: 2; Day 3: 2; Day 4: 1
US-26b | T-40 | Add sourceIds to gtm_agent.py and mvp_agent.py, matching the SWOT pattern | 2026-09-18 | 2026-09-20 | Sashi | Coding | 3- Completed | 3 | Day 5: 3
US-26c | T-41 | Add sourceIds to market_agent.py; extend structured_output.py's validator (deadline Sep 21) | 2026-09-18 | 2026-09-21 | Yasaswini | Coding | 3- Completed | 4 | Day 1: 4
US-26d | T-42 | Extend graph.py's confidence_node into the full confidence-dashboard shape | 2026-09-19 | 2026-09-20 | Yasaswini | Coding | 3- Completed | 4 | Day 4: 2; Day 5: 2
US-27 | T-43 | Build contradiction_detector.py and wire it into graph.py as a new node | 2026-09-21 | 2026-09-23 | Yasaswini | Coding | 3- Completed | 5 | Day 5: 4
US-28 | T-44 | Build experiment_generator.py and action_plan.py | 2026-09-18 | 2026-09-20 | Yasaswini | Coding | 3- Completed | 4 | Day 1: 1; Day 6: 3
US-32 | T-45 | Add advisor decision-history tracking to session_store.py / chat_graph.py | 2026-09-18 | 2026-09-20 | Yasaswini | Coding | 3- Completed | 3 | Day 6: 3
US-29 | T-46 | Build report_assembler.py; update pdf_exporter.py; add report email/GET endpoints | 2026-09-22 | 2026-09-24 | Yasaswini | Coding | 3- Completed | 5 | Day 6: 2; Day 7: 3
US-30 | T-47 | Build citation UI, confidence dashboard, contradictions banner, experiments/action-plan tab | 2026-09-17 | 2026-09-25 | Anu Kumari | Coding | 3- Completed | 6 | Day 7: 3; Day 8: 3
US-31 | T-48 | End-to-end + partial-failure-path test coverage; Render deployment/regression check | 2026-09-25 | 2026-09-30 | Yasaswini | System Test | 3- Completed | 5 | Day 9: 5
US-31 | T-49 | Token-budget/latency measurement pass; document search/retrieval + contradiction detector | 2026-09-25 | 2026-09-30 | Yalene,Yasaswini | Others | 3- Completed | 3 | Day 9: 3
US-31 | T-50 | Final technical documentation, project report, and demo script/recording | 2026-09-25 | 2026-09-30 | Yasaswini | Others | 3- Completed | 4 | Day 10: 4
US-33 | T-51 | Add quick/deep validation-mode flag on POST /validate + concurrent-LLM-call limiting | 2026-09-25 | 2026-09-30 | Yalene, Yasaswini | Coding | 3- Completed | 4 | Day 10: 4
SPRINT 5 BACKLOG
US-34 | T-52 | Fix Wikidata enrichment 403 (add required User-Agent header) + add iTunes Search API enrichment | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 2 | Day 1: 2
US-35 | T-53 | Add CEO-bio-line, review-byline, and scraped-byline-merge NER filters (KhanWritten/GirdharLast-style artifacts) | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 3 | Day 1: 3
US-36 | T-54 | Add deterministic direct/indirect classification heuristic for NER-found competitors (was hardcoded 'unknown') | 2026-09-29 | 2026-09-30 | Yasaswini | Coding | 3- Completed | 2 | Day 1: 2
US-38 | T-55 | Fix dead gemini-2.5-flash fallback reference and competitor-discovery max_tokens exceeding Groq's per-model cap | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 2 | Day 1: 2
US-39 | T-56 | Fix mvp_node/gtm_node clobbering the errors dict instead of preserving prior nodes' failures | 2026-09-30 | 2026-09-30 | Yasaswini | Coding | 3- Completed | 1 | bar: Day 1
US-37 | T-57 | Blend Tavily + DuckDuckGo in fetch_results so one dominant source can't flood a query's results | 2026-09-30 | 2026-09-30 | Yasaswini | Coding | 3- Completed | 2 | Day 1: 2
US-40 | T-58 | Reconcile local branch (13 commits behind origin/staging) against teammate's parallel competitor fixes; drop redundant/incorrect changes, keep 8 unique fixes | 2026-09-30 | 2026-09-30 | Yasaswini | Others | 3- Completed | 3 | Day 1: 3
US-31 | T-59 | Live end-to-end browser testing on localhost across multiple ideas; diagnosed Groq/Gemini quota exhaustion and Render/Neon cold-start latency | 2026-09-29 | 2026-09-30 | Yasaswini | System Test | 3- Completed | 3 | Day 1: 3
US-41 | T-60 | Verify/document CI pipeline (GitHub Actions: backend unittest discover + frontend lint/build) runs on every push/PR to staging & main | 2026-09-30 | 2026-09-30 | Yasaswini | Others | 3- Completed | 1 | bar: Day 1
US-42 | T-61 | Audit current automated test coverage: 503 backend test functions across 40 files, 18 frontend test files | 2026-09-30 | 2026-09-30 | Yasaswini | Others | 3- Completed | 1 | bar: Day 1
US-47 | T-62 | Write backend/scripts/copy_database.py (env-var driven, dry-run, count verification, refuses non-empty destination) | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 3 | Day 1: 3
US-47 | T-63 | Add 'Moving to Neon' steps to DEPLOYMENT.md; make DATABASE_URL sync:false in render.yaml | 2026-09-29 | 2026-09-29 | Yasaswini | Others | 3- Completed | 1 | bar: Day 1
US-47 | T-64 | Copy Render data to Neon (events 717, jobs 3, sessions 23, users 6, validation_cache 16), verify counts and /health reports postgresql | 2026-09-29 | 2026-09-29 | Yasaswini | System Test | 3- Completed | 2 | Day 1: 2
US-48 | T-65 | Lower bcrypt work factor 12 to 10 with rehash on login; add auth tests | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 2 | Day 1: 2
US-43 | T-66 | Product Hunt lookup: exact case-insensitive name match only (no wrong-company badges) | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 2 | Day 1: 2
US-43 | T-67 | Add similarProducts (max 5) from Product Hunt idea search plus SimilarProducts UI in CompetitorAnalysis.jsx | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 3 | Day 1: 3
US-50 | T-68 | retrieval.py: competitor angle queries lead with unbranded domain terms shared by idea, customer and problem; new tests | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 3 | Day 1: 3
US-50 | T-69 | deterministic_fallback.py: fallback threats quote an offering only if it names the competitor and is not a repeat | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 1 | bar: Day 1
US-49 | T-70 | graph.py: relevance lookup covers all sources (citations beyond src-10 were ignored) | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 2 | Day 1: 2
US-49 | T-71 | graph.py: overall confidence = 40% coverage + 20% agreement + 20% direct evidence + 20% relevance; regression tests | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 2 | Day 1: 2
US-51 | T-72 | main.py: do not cache partial/degraded /validate responses; tests in test_quick_deep_mode.py | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 1 | bar: Day 1
US-44 | T-73 | Replace bucketed competition score with continuous formula; edge-case tests | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 2 | Day 1: 2
US-46 | T-74 | Write docs/load-testing-plan.md, docs/scaling-options.md (incl. Neon comparison), docs/known-limitations-and-future-work.md, competitor/confidence proposal | 2026-09-29 | 2026-09-29 | Yasaswini | Design | 3- Completed | 6 | Day 1: 6
US-41 | T-75 | CI fix: mock the iTunes lookup in EnrichWithApisTests so tests do not call the network (runs 151-152 red, green from run 153) | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 1 | bar: Day 1
US-41 | T-76 | CI fix: update confidence dashboard test expectations to the corroboratedSources shape (runs 124-128) | 2026-09-29 | 2026-09-29 | Yasaswini | Coding | 3- Completed | 1 | bar: Day 1
US-41 | T-77 | Verify CI on staging after each push: runs 153-156 green (unittest discover, 502 backend tests) | 2026-09-29 | 2026-09-29 | Yasaswini | System Test | 3- Completed | 1 | bar: Day 1
US-52 | T-78 | Run Locust load test with 5-6 concurrent users against staging and record results |  |  | Yasaswini | System Test | 3- Completed | 3 | Day 1: 3

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 2026-08-25 | None | Kickoff — aligned on stack (React + Tailwind, FastAPI, Tavily)
Sprint 1 | 2026-08-26 | Initial Tavily integration hit rate limits during testing | Added a free DuckDuckGo/Wikipedia/Hacker News fallback chain to remove the single-provider dependency
Sprint 1 | 2026-08-27 | CrewAI's output_pydantic proved unreliable with the Groq model (tool_use_failed errors) | Switched to a plain-JSON-in-task-description parsing approach with a safe fallback
Sprint 1 | 2026-08-28 | Render-assigned service URLs differed from what was hardcoded in render.yaml | Updated FRONTEND_ORIGIN/VITE_API_URL env vars directly in the Render dashboard
Sprint2 | 2026-02-09 | Found a bug in Opportunity Score calculation when no grounded data was available. | Refactored to fallback model/search-based fallback and currently checking edge cases.
sprint2 | 2026-03-09 | Opportunity Score edge-case testing pending | Completed Opportunity Score edge-case testing. Tested missing data, market signals, trends, competitor density, partial failures and search fallback. All tests passed successfully
Sprint 3 | 2026-09-08 | Competitor NER was mistagging generic single words as company names | Fixed NER tagging and excluded generic competitor-directory aggregator domains from retrieval
Sprint 3 | 2026-09-15 | White-space analysis needed to stay grounded in real evidence without spending another LLM call | Built white_space.py as a deterministic post-processing step reusing the existing market/competitor outputs
Sprint 3 | 2026-09-16 | qwen/qwen3.6-27b (the primary model) was deprecated and removed from Groq mid-development | Switched DEFAULT_MODEL to qwen/qwen3.8-27b and re-confirmed reasoning_effort values live against the new model
Sprint 3 | 2026-09-16 | Two independent Milestone 3 implementations existed on separate branches (yasaswini-ch-project-awareness vs staging) | Merged and reconciled both branches into staging, keeping staging's PDF export
Sprint 4 | 2026-09-17 | None - planning day | Divided the remaining Milestone 4 work (Tracks A-G) across the team with a written timeline and deadlines
Sprint 4 | 2026-09-18 | agent/confidence.py turned out to be dead code - the live /validate response actually uses a separate, differently-shaped confidence_node() inside graph.py | Flagged for reconciliation; the confidence-dashboard extension will build on the live node, not the orphaned module
Sprint 4 | 2026-09-18 | Adding sourceIds to SWOT changed strengths/weaknesses/opportunities/threats from plain strings to objects, silently breaking deterministic_mvp, email_delivery.py, and pdf_exporter.py | Fixed all three call sites and added a regression test that drops any hallucinated source id
Sprint 5 | 2026-09-29 | Wikidata enrichment was silently failing 100% of the time (HTTP 403) with no visible error to the user | Traced to urllib's default User-Agent being blocked by Wikimedia's bot policy; added a descriptive User-Agent header
Sprint 5 | 2026-09-29 | Groq's qwen3.8-27b hard-rejected competitor discovery's LLM call every time regardless of quota (max_tokens exceeded its 1000 output-tokens/minute cap), and the Gemini fallback tier referenced a dead model (gemini-2.5-flash, 404) | Lowered max_tokens to 950 and fixed the fallback chain to use gemini-3.8-flash
Sprint 5 | 2026-09-30 | Sign-in on the deployed app is slow even after migrating the database to Neon | Diagnosed as Render's free-tier web service cold start (15-min sleep, 30-60s wake) compounded by Neon's own autosuspend, not a database or code issue; documented options (paid tier, keep-alive ping, or accept for demo use) for the team to decide
Sprint 5 | 2026-09-29 | Render free Postgres expires Oct 25, 2026 and reads were slow | Moved to Neon free Postgres; wrote a verified copy script; rotated the exposed passwords
Sprint 5 | 2026-09-29 | Groq and Gemini free-tier quotas exhausted, so reports fell back to 'AI unavailable' text | Fallback chain kept; degraded reports no longer cached; a paid Groq tier or second Gemini key is a team decision
Sprint 5 | 2026-09-29 | Two identical reports for the same idea | Found the 30-minute result cache serving a degraded report; stopped caching partial responses
Sprint 5 | 2026-09-29 | Overall confidence showed 0% with 56 sources | Relevance lookup ignored sources beyond src-10 and had a 0.5 cliff; fixed and blended the four signals
Sprint 5 | 2026-09-29 | Competitors for a clinical Spanish app were English-pronunciation apps | Competitor queries now lead with domain terms shared across idea, customer and problem
Sprint 5 | 2026-09-29 | CI red on staging: iTunes tests hit the real API; stale confidence test expectations | Mocked the iTunes lookup; updated test expectations; runs 153-156 green
Sprint 5 | 2026-09-29 | Product Hunt attached a different company's data to a competitor | Exact name match only; separate similar-products list for idea matches

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-08-25 | 2026-08-28 | Yasaswini | Delegating pieces earlier next sprint | Owning nearly the entire pipeline single-handedly | Documenting decisions with the 'why', not just the 'what' | Keep contract-first approach for M2; split work more evenly across the team from day one
2 | 1 | 2026-08-25 | 2026-08-28 | Varshini | Taking a larger share of the agent work |  | Reusing the Tavily integration pattern cleanly | Take full ownership of a whole agent in M2, not just one integration piece
3 | 1 | 2026-08-25 | 2026-08-28 | Anu Kumari | Building more components independently |  | Keeping the ValidationResults display clean and grouped by angle | Own the full frontend surface for new M2 data, not just one component
4 | 2
5
6
7
8 | 3 | 2026-09-08 | 2026-09-16 | Yasaswini | Splitting a milestone across the team as originally planned | Owning an entire milestone single-handedly again - the exact Sprint 1 retro item repeated-- team dynamics relared issues | Documenting fallback/degraded-mode design decisions with their 'why', not just the 'what' | Milestone 4 was explicitly divided across all 5 team members with a written task-division doc, timeline, and per-person deadlines before work started, so Sprint 4 doesn't repeat the pattern
9 | 5 | 2026-09-29 | 2026-09-30 | Yasaswini | Setting clearer task-ownership boundaries so accountability does not default back to me | Absorbing the fallout when other members work breaks production or misses deadlines | Documenting fallback/degraded-mode design decisions with their 'why', not just the 'what' | Same pattern as Sprint 1 and Sprint 3 retros - explicitly flagging this a third time; team to redistribute ownership of production-breaking risk, not just task volume. Verified via git log --numstat (Sept 8-30): 161/186 commits (87%) and +40,864 lines, ~76% of all insertions across Milestones 3-4 combined - not just a feeling, confirmed from commit history
10 | 5 | 2026-09-29 | 2026-09-30 | Varshini | Committing more consistent, focused time to assigned project tasks |  | Reusing established integration patterns cleanly when engaged | Check in with Varshini on task load/blockers each standup rather than only at sprint end
11 | 5 | 2026-09-29 | 2026-09-30 | Anu Kumari | Learning backend/pipeline concepts beyond frontend components, to build broader project fluency |  | Keeping frontend components clean and well-organized | Pair Anu Kumari with a backend owner on one pipeline node next sprint
12 | 5 | 2026-09-29 | 2026-09-30 | Sashi | Testing changes locally and pushing to a feature branch/staging (never main) before merge | Pushing unverified changes directly to main - crashed the backend once and broke the CI/CD pipeline a second time |  | Add branch protection on main requiring passing CI before merge; Sashi to verify tests pass locally before every push
13 | 5 | 2026-09-29 | 2026-09-30 | Yalene | Taking on a larger, more independent share of tasks each sprint |  | Reliable execution on assigned orchestration/partial-failure work | Assign Yalene a full feature area next sprint instead of shared/support tasks